## Project Timeline
# | Day / Phase | Date* | To-Dos | Deliverable | Risk / Note | Status
1 | Day 1 Environment & Data Pipeline | Day 1 | • Set up repo structure & .env (Pinecone, Groq, LangSmith keys) • Build transcript_extractor.py via youtube-transcript-api • Build cleaner.py — merge lines, normalize punctuation, strip sponsors • Build chunker.py — 30–90s semantic/time-window chunks • Add metadata: video_id, title, channel, topic, chunk_id, start, end • Run pipeline on 5 test videos, verify output JSON | Clean chunks.json for 5 videos Validated JSON structure | Caption format varies by channel — test Veritasium, Kurzgesagt early | Done
2 | Day 2 Pinecone Indexing & Corpus | Day 2 | • Build embedder.py — sentence-transformers/all-MiniLM-L6-v2 • Build indexer.py — upsert to Pinecone with metadata • Create namespaces: 'corpus' (pre-built) & 'live' (on-the-fly) • Curate 20–30 videos (Veritasium, Kurzgesagt, Big Think) • Run full pipeline end-to-end, confirm index count in dashboard • Write metadata.json catalog for all indexed videos | Pinecone index populated metadata.json complete | Pinecone free tier: use namespaces, stay in one index | Done
3 | Day 3 RAG Core & Agent | Day 3 | • Build retriever.py — Pinecone similarity search, top-k chunks + sources • Build rag_chain.py — LCEL prompt template + LLM + retriever • Design system prompt: grounded, cites timestamps, says 'I don't know' • Set up LangSmith tracing, verify traces in dashboard • Build agent.py — LangGraph agent with RAGRetrieverTool & VideoMetadataTool • Add ConversationBufferWindowMemory (last 5 turns) • Manual smoke test: 10 questions across 3 videos | python agent.py answers correctly in terminal | ⚠️ CRITICAL PATH — if Day 3 slips, cut eval scope before UI scope | Done
4 | Day 4 Live URL + Streamlit UI | Day 4 | • Build live_ingest.py — URL → extract → clean → chunk → embed → upsert • Handle edge cases: no captions → YouTubeSuggestionTool fallback • Check captions first; if missing, suggest 3–5 similar captioned videos • Scaffold Streamlit app: sidebar (mode selector, catalog), chat area, URL input • Connect Streamlit ↔ agent — basic end-to-end chat working locally | Chat UI on localhost:8501 Both corpus & live modes working | No-caption videos are a demo killer — build suggestion fallback first | Done
5 | Day 5 UI Polish & Evaluation | Day 5 | • Add source citations in chat — video title + timestamp range per answer • Add 'Watch this segment' deep link (?t= param) • Add loading spinner / streaming output (st.write_stream) • Build eval_set.json — 30 manual QA pairs across corpus • Run LangSmith evals: correctness, retrieval relevance, hallucination • Iterate on prompt template based on eval results | Eval results in LangSmith UI presentable | Groq rate limits during eval runs — batch requests, add retry logic | Done
6 | Day 6 Deployment & Docs | Day 6 | • Run prompt-v2-full eval (25 cases) — Groq TPD resets midnight UTC • Compare prompt-v1 vs prompt-v2-full in LangSmith dashboard • Fix VideoMetadataTool exact topic match (exact first, loose fallback) • Smoke test 5 demo questions (moved from Day 5) • Review manual_review.json — 5 adversarial cases manually • Push to GitHub (clean repo, secrets in .env / Streamlit secrets) • Deploy to Streamlit Community Cloud • Set env variables in Streamlit Cloud dashboard • Smoke test production: 10 questions on live URL • Write README.md with architecture diagram + demo GIF • Write ARCHITECTURE.md (architecture, methodology, LangChain usage) • Write DATASET.md (extraction, cleaning, chunking, embedding model) • Add 'Buy Me a Coffee' button in sidebar (20 min task) (Low-Prio) | Public live URL / All docs complete / prompt-v2 eval confirmed in LangSmith | Embedding model cold-start on Streamlit Cloud can be slow — test early Groq daily TPD limit — run eval first thing before any manual testing burns tokens | Done
7 | Day 7 UI Polish & Demo Prep | Day 7 | • Fix VideoMetadataTool metadata list formatting • Dark/light mode CSS fix • 2-column layout with YouTube card pinned right • Corpus expansion to 42 videos ✓ (done Day 6) • Update DATASET.md stats (29→42 videos, ~370→674 vectors) • Record demo GIF for README | UI polished & demo-ready Corpus docs updated Demo GIF in repo | 2-column layout touches streaming render path — test thoroughly before pushing | Done
8 | Day 8 Presentation & Buffer | Day 8 | • Build slides: business case, architecture, live demo, eval results, challenges, next steps • Rehearse demo with 5 reliable test questions • Final checks: LangSmith traces clean, Pinecone index healthy • Pre-record backup demo GIF in case live demo fails | Slides ready Confident live demo | Always have a pre-recorded backup — live demos fail | Done
9–10 | Days 9–10 Optional Future Improvements | Days 9–10 | • Speech recognition — Whisper via Groq API for voice questions • LLM upgrade — swap Groq for GPT-4o or Claude for better quality • Multilingual — test with non-English YouTube videos • Metadata filtering — filter by topic/difficulty in sidebar • Soft usage cap UI (show donation prompt after ~20 queries) | Any of the above if time allows | Only attempt if Days 1–7 are fully complete & deployed | Not in scope
MVP | Minimum Viable Product — Must work on demo day
1. Corpus mode: question → grounded answer with source timestamp 2. Live URL mode: paste URL → ingest → answer questions 3. No-caption fallback: suggest similar captioned videos via YouTube Data API 4. LangSmith: clean traces visible for both flows 5. Deployed at a public URL (not localhost) 6. Memory: conversation works across a 3-turn exchange
* Dates are relative (Day 1 = project start). Adjust to your actual calendar.